## Sprint_Backlog
Use Case or User Story | List of detailed development task | Estimate (hrs) | Actual (hrs) | Sprint # | Percent Complete
User Database Table | Create backend so users can be inserted and read from | 1 | 1 | 1 | 100%
User Registration | Design Registration form, validate user information, and create unit tests for registration functionality | 2 | 2 | 1 | 100%
Hash Passwords | Implement ability to hash passwords and verify that the password is equal to the hash. | 2 | 2 | 1 | 100%
User Login | Design login form, validate user login information and create unit tests for login functionality. | 2 | 2 | 1 | 100%
Login Authorization | Verify user has logged in before accessing certain pages | 0.5 | 1 | 1 | 100%
Profile Database Table | Create backend logic so profiles can be inserted and read from | 2 | 2 | 2 | 100%
Profile Creation | Design profile creation form, validate user inputs and create unit tests for profile creation functionality. | 4 | 3 | 2 | 100%
Messages Database Table | Create backend logic so messages can be inserted and read from | 2 | 3 | 2 | 100%
Sending Messages | Design message form, validate user inputs and create unit tests for sending messages | 4 | 4 | 2 | 100%
Password Requirements | Implement password strength requirements, min characters, uppercase, lowercase, special characters and unit tests for password validation logic | 2 | 2 | 3 | 100%
Match Database Table | Create backend logic so matches can be inserted and read from | 1 | 1 | 3 | 100%
Display users to match with | Design explore page so users can see others profiles, and create unit tests for matching functionality | 4 | 4 | 3 | 100%
Like Database Table | Create backend logic so user likes can be stored | 2 | 4 | 3 | 100%
Like User | Create backend logic so users can like each other and then match | 1 | 3 | 3 | 1000%
DisLike User | Create backend logic so users can dislike a user to not match | 1 | 2 | 4 | 100%
List of matches | Design matches page so users can look through there matches, looks at their conversations. | 4 | 4 | 4 | 100%
Edit Existing Profiles | Create logic so users who already created profiles can edit them | 4 | 2 | 4 | 50%
Google Authentication | User google authenciation so users can login with google | 8 | N/A | N/A | 0%
Date Of Birth Requirements | Create date of birth validation requirements so users under 18 cannot sign up. | 2 | N/A | N/A | 0%